## Sites
Site | Region | BU | Country | UsesNewOTNetworkIP | MonitoredSolarWindsOT | MonitoredSinecNMSOT | InOTvSphere | LocalOTDomainController | OTSubnetCIDR | EffectiveDate | Latitude | Longitude
GEN | Europe | BEA | Switzerland | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE |  | 46.204 | 6.143
TEM | Europe | BEA | Ghana | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE
WES | Europe | BEA | Netherlands | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
BUB | Europe | BEA | Switzerland | TRUE | FALSE | FALSE | TRUE | FALSE | TRUE
BCN | Europe | BEA | Spain | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE |  | 41.385 | 2.173
BES | Europe | BEA | France | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE
AMS | Europe | BEA | Netherlands | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE
TAI | Asia | BEA | China | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
PSG | Asia | BEA | Singapore | TRUE | TRUE | FALSE | FALSE | FALSE | TRUE
RAS | Europe | BEA | Finland | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE |  | 60.17 | 24.94
KAR | Europe | BEA | Poland | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE
BIO | Europe | BEA | Spain | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
ESC | Europe | BEA | Spain | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE |  | 43.362 | -8.418
BRU | Europe | BEA | Austria | FALSE | TRUE | FALSE | FALSE | FALSE |  |  | 47.416 | 15.276
ALT | North America | BNA | Canada | TRUE | TRUE | FALSE | TRUE | FALSE
AMZ | South America | BSA | Brazil | FALSE | TRUE | FALSE | FALSE | FALSE
XMN | Asia | BEA | China | TRUE | FALSE | FALSE | TRUE | FALSE |  |  | 24.479 | 118.089
NMU | South America | BSA | Brazil | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
RDN | South America | BSA | Brazil | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
LEM | South America | BSA | Brazil | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
RGR | South America | BSA | Brazil | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
PGR | South America | BSA | Brazil | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
PGM | South America | BSA | Brazil | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
TTI | South America | BSA | Brazil | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE
LUZ | South America | BSA | Brazil | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE
URU | South America | BSA | Brazil | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE
DRD | South America | BSA | Brazil | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE
SJS | South America | ARG | Argentina | TRUE | FALSE | FALSE | TRUE | FALSE | TRUE
PSGM | South America | ARG | Argentina | TRUE | FALSE | FALSE | TRUE | FALSE | TRUE

## Tasks
Site | TaskId | TaskName | TaskType | Status | PlannedDate | CompletedDate
BRU | Control System | PLC Migration | Replaced legacy extraction PLCs with Siemens S7-410H controllers. | Completed | 30-09-2024 | 2025-01-01
BRU | Network Infrastructure | Engineering Network Preparation | Prepared new network and power cabling for PLCs and engineering stations. | Completed | 30-09-2024 | 2025-01-01
BRU | Virtualization | Engineering Station Virtualization | Planned virtualization of engineering station on OT server cluster. | Completed | 30-09-2024 | 2025-01-01
BRU | Control System | SCADA Redundancy | Implemented and tested WinCC redundancy and diagnostic features. | Completed | 30-09-2024 | 2025-01-01
BRU | Backup & Documentation | System Backups & Testing | Created backups of PLC and SCADA projects; tested communication and failover scenarios. | Completed | 30-09-2024 | 2025-01-01
BRU | Network Infrastructure | OT Network Consolidation | Migrated three plant networks into a single OT network (VLAN 806) and reconfigured gateways/subnets. | Completed | 30-09-2024 | 2025-01-01
BRU | Security | Firewall Migration | Removed legacy Cisco firewall and integrated OT network into Check Point firewall for DMZ access. | Completed | 30-09-2024 | 2025-01-01
BRU | Networking | Switch Replacement | Replaced unknown managed switches with new switches to simplify network management. | Completed | 30-09-2024 | 2025-01-01
GEN | Access Control | Access Control | Deployed RADIUS/NPS servers for OT switch authentication. | Completed | 30-09-2024 | 2025-01-01
RIZ | Monitoring | Monitoring | Integrated Level 2 switches into SolarWinds. | Completed | 30-09-2024 | 2025-01-01
TAI | Networking | Core Network | Replaced aging OT switch stack with Cisco 9500 series. | Completed | 30-09-2024 | 2025-01-01
ESC | Virtualization | OT Virtualization | Built new OT VMware Cluster ESC_OT_SV2_EVC with redundant 10Gb links and new VLAN 2132 storage network. | Completed | 30-09-2024 | 2025-01-01
ESC | Networking | Network Infrastructure | Configured 8 new Cisco IE3300 L2 switches for OT Level 2 connectivity and redundancy. | Completed | 30-09-2024 | 2025-01-01
ESC | Security | Endpoint Security | Removed SEP/SentinelOne from OT servers and re-routed Defender logs via SCCM through OT FW. | Completed | 30-09-2024 | 2025-01-01
ESC | Monitoring | Monitoring | Integrated all OT L2 switches into SolarWinds and deployed RADIUS/NPS authentication via GEN servers. | Completed | 30-09-2024 | 2025-01-01
ESC | Security | Firewall Segmentation | Migrated legacy VLAN gateways to Check Point OT firewalls (VRRP config). | Completed | 30-09-2024 | 2025-01-01
BCN | Virtualization | Virtualization | Migrated all OT VMs from IT vSphere to new OT SimpliVity cluster. | In Progress | 30-09-2024 | 2025-01-01
BCN | Networking | Core Network | Created new 10 Gb uplinks from ESX04 to OT Core; rerouted legacy VLANs to new Core. | In Progress | 30-09-2024 | 2025-01-01
BCN | Access Control | VLAN Configuration | Configured VLAN 2101 for host-to-host OT VMkernel connectivity; reduced traffic through IT FW. | In Progress | 30-09-2024 | 2025-01-01
BCN | Networking | Network Infrastructure | Replaced old managed/unmanaged switches; consolidated VLAN 818/819 configurations across ISW-03/04. | In Progress | 30-09-2024 | 2025-01-01
BIO | Security | Firewall Upgrade | Installed Check Point 9100 OT firewall cluster replacing legacy IT/OT segmentation. | Completed | 30-09-2024 | 2025-01-01
BIO | Networking | Core Network | Installed new OT Core switches with redundant 10 Gb links. | Completed | 30-09-2024 | 2025-01-01
BES | Troubleshooting | Network Troubleshooting | Verified multicast communication (IGMP snooping / PIM) for OPC servers. | Completed | 30-09-2024 | 2025-01-01
BES | Security | Firewall Configuration | Adjusted FW rules (port 4862/4863) to restore OPC data exchange between servers. | Completed | 30-09-2024 | 2025-01-01
GEN | Monitoring | Monitoring | Deployed SINEC NMS central platform for cross-site L2 switch visibility. | Completed | 30-09-2024 | 2025-01-01
GEN | Infrastructure | Backup Infrastructure | Implemented new OT backup system and firewall rules for 3.5 OT scope. | Completed | 30-09-2024 | 2025-01-01
GEN | Automation | Middleware Development | Created NetBox middleware for Cisco/Siemens device auto-sync. | Completed | 30-09-2024 | 2025-01-01
BRU | Networking | VLAN Segmentation | Reconfigured VLANs 818/819 across ISW-03/04, corrected port assignments for PLC and server connectivity. | Completed | 30-09-2024 | 2025-01-01
BRU | Networking | Switch Replacement | Replaced unknown managed switches with new ones to simplify management. | Completed | 30-09-2024 | 2025-01-01
BRU | Security | Firewall Migration | Removed legacy Cisco firewall and integrated OT network into Check Point DMZ firewall. | Completed | 30-09-2024 | 2025-01-01
RAS | Networking | Core Network | Completed OT infrastructure upgrade and server reservations. | Completed | 30-09-2024 | 2025-01-01
TAI | Networking | Core Network | Configured Process FW with redundancy and connected OT Domain Controller and Jump Server. | Completed | 30-09-2024 | 2025-01-01
XMN | Networking | Core Network | Deployed Red Hat VMs for OCOC application connectivity to OT Core. | Completed | 30-09-2024 | 2025-01-01
RIZ | Monitoring | Monitoring | Integrated L2 switches into SolarWinds for regional visibility. | Completed | 30-09-2024 | 2025-01-01
KRI | Infrastructure | OT Upgrade | Defined and reserved OT infrastructure for future migration. | Completed | 30-09-2024 | 2025-01-01
TEM | Infrastructure | OT Upgrade | Completed definition and reservation for new OT infrastructure upgrade. | Completed | 30-09-2024 | 2025-01-01
KAR | Monitoring | Data Connectivity | Deployed MRI Monitoring VMs (KARNTMRI01/02) and configured USB-over-Ethernet interface. | Completed | 30-09-2024 | 2025-01-01
WES | Networking | Core Network | Configured full L2 OT network with redundant Process FW and domain services. | Completed | 30-09-2024 | 2025-01-01
BUZ | Networking | Core Network | Planned migration of legacy switches and firewall to standardized OT architecture. | Completed | 30-09-2024 | 2025-01-01
ESC | Security | Access Management | Created isolated Proof of Concept (POC) environment for testing OT CyberArk within ICS policy. | Completed | 30-09-2024 | 2025-01-01
ESC | Core Network | OT Redundant Star Topology | Defined and validated redundant star topology design for OT Cisco IE3300 switches to replace legacy core network. | Completed | 30-09-2024 | 2025-01-01
ESC | Monitoring | Nozomi Implementation Preparation | Prepared network span design and topology for Nozomi OT visibility solution using mirrored uplinks from Cisco IE3300 switches. | Completed | 30-09-2024 | 2025-01-01
ESC | Network Documentation | OT Network Documentation and Audit Support | Developed complete OT network diagram and fiber patch panel mapping for ESC site audit. | Completed | 30-09-2024 | 2025-01-01
ESC | Virtualization | OT Cluster Migration | Migrated all SCADA and OT servers from IT cluster (ESX10/11) to new OT cluster (ESX110/112). | Completed | 30-09-2024 | 2025-01-01
ESC | Core Network | OT Network Modernization | Replaced legacy switches with Cisco IE3300 models, validated configurations, and created full switch backups. | Completed | 30-09-2024 | 2025-01-01
ESC | Asset Management | OT Network Inventory Integration | Prepared for full NetBox integration by aligning network topology and device inventory. | Completed | 30-09-2024 | 2025-01-01
ESC | Cabling | OT Cabling Installation | Installed new structured cabling across process areas (Calderas, Water Treatment, Electrical Rooms, Prep 400). | Completed | 30-09-2024 | 2025-01-01
ESC | Core Network | OT Switch Stack Replacement | Replaced aging OT switch stack with Cisco 9500 series core switches. | Completed | 30-09-2024 | 2025-01-01
ESC | Core Network | Backbone Fiber Replacement | Replaced backbone fiber between OT server rooms to support new Cisco core. | Completed | 30-09-2024 | 2025-01-01
ESC | Security | Firewall Replacement | Removed old Cisco firewall exposed to vulnerabilities; integrated OT network with Check Point firewall. | Completed | 30-09-2024 | 2025-01-01
ESC | Monitoring | Nozomi Network Visibility | Implemented Nozomi Guardian and SPAN configuration on new Cisco switches. | Completed | 30-09-2024 | 2025-01-01
ESC | Documentation | Network Diagram & FO Audit | Verified and updated all active fiber-optic connections, created network diagram and patch-panel layout. | Completed | 30-09-2024 | 2025-01-01
ESC | Legacy Migration | Legacy Star Network Migration | Planned migration of legacy redundant star topology to new Cisco IE3300 hardware with full validation. | Completed | 30-09-2024 | 2025-01-01
BCN | Core Network | OT Switch Replacement | Planned replacement of legacy OT switches with Cisco IE3300 series, preparing redundant star topology. | Completed | 30-09-2024 | 2025-01-01
BCN | Monitoring | Nozomi Network Visibility | Prepared topology and SPAN configuration plan for Nozomi OT network monitoring integration. | Completed | 30-09-2024 | 2025-01-01
BCN | Network Documentation | OT Network Topology & Fiber Audit | Documented active fiber connections, created topology and patch panel layout for OT network. | Completed | 30-09-2024 | 2025-01-01
BCN | Network Infrastructure | Legacy Network Assessment | Performed network assessment of legacy OT core and IT firewall routing for migration to new design. | Completed | 30-09-2024 | 2025-01-01
BCN | Project Planning | Shutdown Migration Plan | Defined execution and testing plan for OT switch replacement and VLAN consolidation during plant shutdown. | Completed | 30-09-2024 | 2025-01-01
BCN | Network Infrastructure | Cabling Installation | Completed structured cabling in Cogeneration, Boilers, and Water Treatment; pending two points in Electrical Room 2200 (requires de-energization). | Completed | 30-09-2024 | 2025-01-01
BCN | Network Infrastructure | Cabling Installation | Installed cabling/conduits for new network points in Electrical Room 2700 and Prep 400 to onboard OT assets. | Completed | 30-09-2024 | 2025-01-01
BCN | Network Infrastructure | OT Network Deployment (ICS) | Prepared switch configurations, UPS integrations, and network readiness verification for OT rollout. | Completed | 30-09-2024 | 2025-01-01
BCN | Network Infrastructure | Commissioning & Verification | Planned on-site verification of installed network points and quality checks before cutover. | Completed | 30-09-2024 | 2025-01-01
ALT | Network Infrastructure | OT Network Deployment (ICS) | Prepared switch configurations, UPS integrations, and network readiness verification for OT rollout. | Completed | 30-09-2024 | 2025-01-01
AMZ | Network Infrastructure | Commissioning & Verification | Planned on-site verification of installed network points and quality checks before cutover. | Completed | 30-09-2024 | 2025-01-01

## Projects
Site | ProjectType | ProjectId | BeforeState | AfterState | KeyBenefits | Status | PlannedDate | CompletedDate
BRU | Full ICS | PLC Migration | Legacy Siemens S5/older controllers, frequent downtime | Siemens S7-410H redundant controllers, modern diagnostics | Reliability↑, Redundancy↑, Maintainability↑ | Completed |  | 2025
GEN | Regional Monitoring | Monitoring Upgrade | Inconsistent visibility, manual checks | Centralised monitoring via SolarWinds | Visibility↑ | Completed |  | 2024
XMN | OT Upgrade | Core Network Refresh | Single core switch, no redundancy | Dual core, 10G uplinks, segmented | Bandwidth↑;Resilience↑ | Completed |  | 2025
BCN | Minimum ICS | New OT Network | Flat VLANs, no firewall | Segmented VLANs, Check Point FW, jump server | Security↑;Policy Compliance↑ | In Progress |  | 2025
ESC | Full ICS | OT Redundant Star Topology | Aging access rings, mixed vendors | Cisco IE3300 star with redundant cores | Reliability↑;Standardization↑ | Completed |  | 2024
RAS | POC | OT Visibility | Limited metrics | Standardized Linux agents, central ops | OperationalInsights↑ | Completed |  | 2024
ALT | Full ICS | OT Redundant Star Topology | Aging access rings, mixed vendors | Cisco IE3300 star with redundant cores | Reliability↑;Standardization↑ | Completed |  | 2024
AMZ | Full ICS | OT Visibility North Asia | Limited metrics | Standardized Linux agents, central ops | OperationalInsights↑ | Completed |  | 2024

## KPI
Dimension | Key | Metric | Year | Value